## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Item ID | User Stories / Bugs
|  |  | Initial Estimate (hrs) | Day 1 (hrs) | Day 2 (hrs) | Day 3 (hrs) | Day 4 (hrs) | Day 5 (hrs) | Day 6 (hrs) | Day 7 (hrs) | Day 8 (hrs) | Day 9 (hrs) | Day 10 (hrs)
|  | Example comment section | 1 |  | 1
|  | Create favicon for website | 1 |  | 1
|  | Create navigation bar | 2 |  | 1
|  | Set up a placeholder homscreen | 5 |  | 2
|  | Set up a placeholder individual movie page with fake data | 2 |  |  |  | 1
|  | Work on burndown chart | 2 |  |  | 1
|  | Make movie descriptions around a similar length | 2 | [7 empty] | 2
|  | Make a state diagram for 1 class | 1 |  | 1
|  | Make a UML sequence diagram for an important use case | 2 | [8 empty] | 2
|  | Put placeholder movie posters on website | 3 |  |  | 1
|  | Commit Documentation | 1 | [9 empty] | 1
|  | Commit source code | 2 | [8 empty] | 1
|  | Plan entirety of Iteration 1 agenda | 3 | 1 |  |  |  |  | 2
|  | Actual Time Worked | 18 | 1 | 6 | 2 | 1 | 0 | 2 | 0 | 2 | 3 | 1
|  | Plotted Time | 27 | 17 | 11 | 9 | 8 | 8 | 6 | 6 | 4 | 1 | 0
|  | Estimated Ideal Trend | 27 | 24.3 | 21.6 | 18.9 | 16.2 | 13.5 | 10.8 | 8.1 | 5.4 | 2.7 | 4.4409e-15