## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Item ID | User Stories / Bugs
|  |  | Initial Estimate (hrs) | Day 1 (hrs) | Day 2 (hrs) | Day 3 (hrs) | Day 4 (hrs) | Day 5 (hrs) | Day 6 (hrs) | Day 7 (hrs) | Day 8 (hrs) | Day 9 (hrs) | Day 10 (hrs)
|  | Set up the movie database | 2 |  | 4
|  | Run testing on the program | 2 |  |  | 3
|  | Work on burndown chart | 1 |  | 1
|  | Finish up iteration 1 retrospective | 1 |  | 1
|  | Create unit tests for 2 classes | 3 |  |  | 4
|  | Search function | 3
|  | Get accounts up and running | 4 |  |  | 4
|  | Admin account with privileges | 3
|  | Create build files and ANT scripts | 2 |  |  |  |  | 2
|  | Create documentation for running those files | 1 |  |  |  | 1
|  | Create tests for a feature yet to be implemented | 3 |  |  | 1
|  | Every gorup member submitting something to github | 1 | [9 empty] | 1
|  | Plan entirety of Iteration 2 agenda | 3 | 2
|  | Actual Time Worked | 24 | 2 | 6 | 12 | 1 | 2 | 0 | 0 | 0 | 0 | 1
|  | Plotted Time | 29 | 22 | 16 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0
|  | Estimated Ideal Trend | 29 | 26.1 | 23.2 | 20.3 | 17.4 | 14.5 | 11.6 | 8.7 | 5.8 | 2.9 | 4.4409e-15